## Slide 1: Timetable for PhD
Pascal

## Slide 2: ToDo’s
Unfold with systematics on-going end February
  Effective area
Update wiki page this week next week
WG review (Dennis Soldin) on-going end February
Technical review (Karolin Hymon) March March
The analysis call end March mid April
  Collaboration review
Unblinding End April mid Mai
Write thesis on-going end Mai
Phd Defense end July
Forward fit?
Start End

## Slide 3: Next Steps
Work on unfolding ?
  Systematics
  Effective area
Update wiki 25./26.01.
Answer WG review 31.01.
Present in WG 04.02.
Thesis outline 28.01.